# StudyHub — Sprint 1 Execution Plan (Foundation & Identity)

Course: CPEPE361 (Software Development 1)
Phase: Midterm Phase — Sprint 1 Review (Walking Skeleton Baseline)
Sprint Duration: 2 Weeks (Weeks 6–7)
Development Lifecycle: Sprint 1 of 3

- Sprint 1 (Midterm): Foundation, Identity & Primary CRUD (Walking Skeleton)

- Sprint 2 (Prefinal): Space Discovery & Snap-Grid Seat Map Builder

- Sprint 3 (Final): Exact-Seat Holds, Sandbox Payments, Check-in & Moderation
Status: Planning & Review Baseline

## 1. Sprint Goal & Walking Skeleton Baseline

Deliver the official Walking Skeleton Baseline for StudyHub as mandated by the CPEPE361 Midterm Phase specification:

- Managed Database Connection: Supabase PostgreSQL with robust schemas, automated trigger functions, and Row-Level Security (RLS) enforcement.

- Multi-Role Authentication: Supabase Auth with custom user roles (seeker, host, admin), Row-Level Security as the security boundary, and Next.js SSR session refresh and route redirects in proxy.ts.

- Primary End-to-End CRUD Flows:

  - User Profile CRUD: View and edit user personal info, contact numbers, and preferences.

  - Host Space Listing CRUD: Host creation, viewing, updating, and deletion of basic study hub/co-working venue details (name, location, description, operating hours, base hourly rate, and amenity tags).

- Accessible UI Shell: Next.js 16 App Router layout, WCAG 2.1 AA compliant design tokens, and shadcn/ui accessible primitives (built on Base UI).

- Quality Assurance: Automated Vitest unit test suite covering input validation schemas and RBAC route guard logic.

## 2. Team Workload & Domain Distribution

| Developer | Role & Primary Domain | Story Responsibility & Deliverables |
| --- | --- | --- |
| Adrian Seth Tabotabo | Backend Lead & Database Architect | STORY-01 & STORY-05: Database migrations (profiles, spaces tables, user_role ENUM), RLS policies, trigger handle_new_user(), seed data fixtures, pgTAP policy tests, Space Listing backend Server Actions. |
| Maria Faith Antigua | Frontend Design System Lead | STORY-02: Next.js App Router config, Tailwind 4 token system in the @theme block of app/globals.css (WCAG 2.1 AA contrast ≥4.5:1, ≥48px touch targets), shadcn/ui accessible primitives on Base UI (Button, Input, Label, Card, Badge, Alert), public landing hero, navbar, and footer. |
| Luke Miguel Dongque | Auth & Security Specialist | STORY-03 & STORY-06: Authentication interfaces (/login, /register), interactive Seeker vs. Host role selector card, client & server Zod validation schemas, root proxy.ts session guard, with RLS as the security boundary; Vitest unit testing suite and Playwright smoke tests. |
| James Niño Mandawe | Portal Shells & QA Engineer | STORY-04 & STORY-05 (pages): Authenticated Seeker dashboard layout (/seeker), profile view/update form, Host portal layout (/host) and space listing forms, DoD compliance verification. |

## 3. Product Backlog with MoSCoW Prioritization

To satisfy the CPEPE361 Prelim & Midterm requirements, the product features are categorized using MoSCoW prioritization, clearly delineating Sprint 1’s walking skeleton from Sprint 2 and Sprint 3 deliverables:

| Priority | Feature / User Need | Target Sprint | Description |
| --- | --- | --- | --- |
| Must Have (M) | Multi-Role Authentication | Sprint 1 | Email/password login and registration with explicit role selection (seeker vs. host), blocking client escalation to admin. |
| Must Have (M) | Database Schemas & Row-Level Security | Sprint 1 | PostgreSQL tables for profiles and spaces with 1:1 user links, cascade deletes, and RLS preventing cross-tenant mutation. |
| Must Have (M) | RBAC Route Guard Middleware | Sprint 1 | Server-side session verification protecting /seeker/*, /host/*, and /admin/* routes from unauthorized roles. |
| Must Have (M) | Primary CRUD 1: User Profile Management | Sprint 1 | Seekers and Hosts can read and update their own full name, phone number, and preferences. |
| Must Have (M) | Primary CRUD 2: Host Space Listing CRUD | Sprint 1 | Hosts can create, view, update, and delete basic study space listings (name, address, rate, hours, amenities). |
| Should Have (S) | WCAG 2.1 AA Design System & Shell | Sprint 1 | Accessible color tokens, keyboard navigation focus rings, mobile-responsive layout, and public landing hero. |
| Should Have (S) | Automated Unit Testing Suite | Sprint 1 | Vitest test coverage for auth form validations, password constraints, and role-guard redirection logic. |
| Should Have (S) | Test Data Seeding | Sprint 1 | seed.sql script with reproducible Admin, Host, and Seeker accounts and sample venue records. |
| Could Have (C) | Amenity Multi-Select Badges | Sprint 1 | Interactive toggles for Wi-Fi speed tier, power outlet accessibility, aircon, and quiet zone tags on space listings. |
| Could Have (C) | Admin Console Shell | Sprint 1 | Read-only administrative dashboard displaying registered user counts and database health metrics. |
| Won’t Have (W) | Interactive Snap-Grid Seat Map Builder | Sprint 2 | Visual canvas/grid for hosts to place desks, power sockets, and zones (deferred to Sprint 2). |
| Won’t Have (W) | Live Geo-Search & Interactive Map | Sprint 2 | Leaflet/OpenStreetMap discovery with live distance calculation and amenity filtering (deferred to Sprint 2). |
| Won’t Have (W) | Image Storage & Venue Photo Uploads | Sprint 2 | Supabase Storage bucket integration for space photography (deferred to Sprint 2). |
| Won’t Have (W) | Reserve-Now Seat Holds & Timed Locks | Sprint 3 | Atomic PostgreSQL transaction holding open seats, with a payment window and a seeker-set wait window (deferred to Sprint 3). |
| Won’t Have (W) | Sandbox Reservation Fee Payments | Sprint 3 | Mock payment gateway with forfeiture on no-show and admin refund workflows (deferred to Sprint 3). |
| Won’t Have (W) | QR Check-in & Review Moderation | Sprint 3 | Host QR scanner verification and moderation dispute console (deferred to Sprint 3). |

## 4. Sprint 1 User Stories & Task Decomposition

In accordance with the CPEPE361 Task Decomposition Spec, every user story includes an identifier, agile user narrative, story point estimate (scale 1–10), time estimate, a single assigned owner, a Git branch prefix, granular task breakdown, and acceptance criteria. Each story starts with a merged design doc on feature/STORY-xx-design, and each task then ships as its own pull request from its own feature/STORY-xx-short-desc branch.

### [STORY-00] Repository Foundation & Team Conventions

- Story: As a team, we want a configured repository, an agreed workflow, and a working scaffold, so that every later story starts from the same baseline.

- Story Points: 5 / 10

- Time Estimate: 3 Days

- Assignee: Adrian Seth Tabotabo

- Git Branch: feature/STORY-00-short-desc (one per task)

- MoSCoW: Must Have

#### Granular Tasks:

- TSK-00.1 (#61) Configure repository settings and the two main rulesets.

- TSK-00.2 (#62) Rebuild the project board, labels, milestones, and story issues.

- TSK-00.3 (#63) Move the course documents into docs/course/ — merged (PR #68).

- TSK-00.4 (#64) Scaffold Next.js 16, shadcn/ui, Supabase, and CI — merged (PR #69).

- TSK-00.5 (#65) Add AGENTS.md, the decisions log, the glossary, and the templates.

- TSK-00.6 (#66) Add the onboarding, development, and team guides.

- TSK-00.7 (#67) Align the Sprint plan, README, and worksheet with the SRS and the decisions.

#### Acceptance Criteria:

- main is protected, and every change lands through a reviewed, squash-merged pull request.

- npm run check and npm run build pass on a fresh clone.

- No document in the repository contradicts the SRS or the decisions log.

### [STORY-01] Foundation, Database Schemas & Row-Level Security

- Story: As a developer, I want a robust Supabase PostgreSQL schema with RLS and automated triggers, so that user profiles and space listings are securely isolated and persisted.

- Story Points: 8 / 10

- Time Estimate: 3 Days

- Assignee: Adrian Seth Tabotabo

- Git Branch: feature/STORY-01-database-rls

- MoSCoW: Must Have

#### Granular Tasks:

- Bind the Supabase environment variables already scaffolded in STORY-00 (NEXT_PUBLIC_SUPABASE_URL, NEXT_PUBLIC_SUPABASE_PUBLISHABLE_KEY; SUPABASE_SECRET_KEY stays server-only).

- Write migration 20260914000001_init_auth_and_profiles.sql defining user_role ENUM (seeker, host, admin) and public.profiles table linked 1:1 to auth.users(id).

- Implement handle_new_user() PostgreSQL trigger function extracting role metadata upon signup and sanitizing against client-side admin self-promotion.

- Define public.spaces table with fields: id, host_id (FK to profiles), name, description, address, hourly_rate, operating_hours, amenities (text array), status, and timestamps.

- Configure Row-Level Security (RLS) policies:

  - profiles: Public select, self-update only, admin full oversight.

  - spaces: Public select for active spaces, host insert/update/delete restricted to host_id = auth.uid().

- Create supabase/seed.sql with reproducible invented test accounts (admin@example.test, seeded locally only, host@example.test, seeker@example.test).

- Generate TypeScript database definitions with npm run db:types (lib/supabase/database.types.ts).

- Add the Supabase SSR client factories (lib/supabase/client.ts, lib/supabase/server.ts) that STORY-03, STORY-04 and STORY-05 build on.

#### Acceptance Criteria:

- Database migration executes cleanly without warnings or foreign-key anomalies.

- RLS rejects any unauthorized cross-account profile update attempt.

- User signup automatically creates a matching row in public.profiles.

### [STORY-02] Accessible Design System & Public Shell

- Story: As a public visitor, I want an accessible, responsive landing page and clean UI components, so that I can understand StudyHub’s value proposition and navigate seamlessly.

- Story Points: 5 / 10

- Time Estimate: 2 Days

- Assignee: Maria Faith Antigua

- Git Branch: feature/STORY-02-design-system

- MoSCoW: Should Have

#### Granular Tasks:

- Configure Tailwind 4 design tokens in the @theme block of app/globals.css, ensuring WCAG 2.1 AA compliance with minimum 4.5:1 text contrast.

- Add accessible shadcn/ui primitives on Base UI (npx shadcn add): Button, Input, Label, Card, Badge, Alert, with visible keyboard focus rings.

- Build responsive public navigation header with dynamic login/register state.

- Build landing page (/) showcasing StudyHub’s 3 core value pillars:

  - Live Snap-Grid Map (interactive seat view preview).

  - Verified Amenities (Wi-Fi tiers, power outlets, quiet zones).

  - Reserve-Now Holds (guaranteed seat upon arrival).

- Build accessible, semantic footer with platform disclaimers and navigation links.

#### Acceptance Criteria:

- All interactive elements maintain touch targets ≥48px×48px.

- Keyboard navigation (Tab, Shift+Tab, Enter, Space) operates with visible focus indicators.

- Landing page renders responsively on mobile (360px), tablet (768px), and desktop (1024px) without horizontal scrolling.

### [STORY-03] Multi-Role Authentication, Registration & RBAC Middleware

- Story: As a user, I want to register as either a Seeker or a Host and log in securely, so that I am authenticated and routed to my role-specific dashboard with protected access.

- Story Points: 8 / 10

- Time Estimate: 3 Days

- Assignee: Luke Miguel Dongque

- Git Branch: feature/STORY-03-auth-rbac

- MoSCoW: Must Have

#### Granular Tasks:

- Build the session helper lib/supabase/proxy.ts on STORY-01’s client factories (lib/supabase/client.ts, server.ts).

- Build Zod validation schemas (lib/validation/auth.ts) validating email formats, password complexity (≥8 chars, numbers, symbols), and role selection.

- Build /login page with reactive client state, loading indicators, and error alert banners.

- Build /register page featuring an interactive Role Selector Card (Seeker vs. Host) with contextual explanatory copy.

- Implement root proxy.ts (Next 16’s replacement for middleware.ts), refreshing the session and applying RBAC redirects, with RLS as the real boundary:

  - Anonymous users attempting to access /seeker/*, /host/*, or /admin/* are redirected to /login.

  - Logged-in Seekers accessing /host/* or /admin/* are routed back to /seeker.

  - Logged-in Hosts accessing /admin/* or /seeker/* are routed back to /host.

- Implement safe post-login redirection based on authenticated user role.

#### Acceptance Criteria:

- Unauthenticated requests to /seeker, /host, or /admin redirect to /login with a returnUrl parameter.

- Seeker registration assigns seeker role; Host registration assigns host role.

- Role escalation via tampered request metadata is rejected at the database trigger layer.

### [STORY-04] Seeker Portal & User Profile CRUD

- Story: As a Seeker, I want to access my personal dashboard and view/update my profile details, so that my account information and contact preferences remain accurate.

- Story Points: 5 / 10

- Time Estimate: 2 Days

- Assignee: James Niño Mandawe

- Git Branch: feature/STORY-04-seeker-profile-crud

- MoSCoW: Must Have

#### Granular Tasks:

- Build authenticated dashboard shell (app/(dashboard)/seeker/layout.tsx and components/dashboard-header.tsx).

- Construct Seeker dashboard view (app/(dashboard)/seeker/page.tsx) showing account status, role badge, and quick stats.

- Implement Profile Edit form allowing users to update their full_name, phone_number, and study preference tags.

- Wire form submission to Supabase profiles table update action with optimistic UI state and toast/alert feedback.

- Display informational placeholder cards highlighting upcoming Sprint 2 (Search Spaces) and Sprint 3 (Active Reservations) features.

#### Acceptance Criteria:

- Profile details load automatically for the currently logged-in user.

- Updating full name or phone number persists immediately to the database and reflects upon page refresh.

- Attempts to alter user ID or role during update are rejected.

### [STORY-05] Host Portal & Space Listing CRUD

- Story: As a Host, I want to create, view, edit, and delete basic study space listings in my portal, so that I can represent my venue to prospective seekers.

- Story Points: 8 / 10

- Time Estimate: 3 Days

- Assignee: Adrian Seth Tabotabo

- Git Branch: feature/STORY-05-host-space-crud

- MoSCoW: Must Have

#### Granular Tasks:

- Build Host portal shell (app/(dashboard)/host/layout.tsx) with host navigation and logout button.

- Build Host space management dashboard (app/(dashboard)/host/page.tsx) listing all spaces owned by the authenticated host.

- Implement “Create Space Listing” modal/form:

  - Space Name (text, required).

  - Address / Location (text, required).

  - Description (textarea).

  - Operating Hours (text, e.g., “7:00 AM - 11:00 PM”).

  - Base Hourly Rate (numeric, PHP).

  - Amenity Checkbox Tags (High-Speed Wi-Fi, Dedicated Outlets, Air Conditioning, Quiet Zone).

- Implement “Edit Space Listing” dialog allowing hosts to modify existing listing details.

- Implement “Delete Space” confirmation dialog ensuring safe deletion of unneeded listings.

- Enforce RLS verification ensuring hosts can neither view unapproved draft listings of other hosts nor modify other hosts’ venues.

#### Acceptance Criteria:

- Host can create a new space listing and see it appear immediately in their space list.

- Host can update the name, rate, or amenities of their own listing.

- Host can delete their listing with confirmation.

- Non-owners cannot edit or delete spaces belonging to another host.

### [STORY-06] Automated Unit Testing & QA Verification Suite

- Story: As a QA engineer, I want automated unit tests for validation schemas and route guard logic, so that our codebase maintains high reliability and passes the Definition of Done.

- Story Points: 5 / 10

- Time Estimate: 2 Days

- Assignee: Luke Miguel Dongque

- Git Branch: feature/STORY-06-testing-qa

- MoSCoW: Should Have

#### Granular Tasks:

- Extend the Vitest harness scaffolded in STORY-00 (vitest.config.mts).

- Write unit tests for the authentication validation schemas next to the code (lib/validation/auth.test.ts):

  - Validates valid email, weak passwords (< 8 chars, missing numbers), and role enumeration.

- Write unit tests for the RBAC route guard logic next to the code (lib/auth/role-guard.test.ts):

  - Tests unauthenticated redirection to /login.

  - Tests Seeker access permissions (allow /seeker, deny /host, deny /admin).

  - Tests Host access permissions (allow /host, deny /seeker, deny /admin).

  - Tests Admin access permissions across all portals.

- Write validation tests for Space Listing schema (ensuring positive rates, non-empty titles).

- Run the repository checks before every push: npm run check (typecheck, lint, format check, unit tests) and npm run db:test (pgTAP policy tests).

#### Acceptance Criteria:

- npm run check passes (typecheck, lint, format check, and all Vitest unit tests).

- npm run db:test passes (pgTAP policy tests, including the negative tests).

- npm run build succeeds, matching the checks job in CI.

## 5. Project Management Board Mapping (GitHub Projects)

In compliance with the CPEPE361 brief, below is the visual state mapping of all user story cards across the 5 required project board columns:

StudyHub CPEPE361 Project Management Board

(Interactive version with HTML summary cards: StudyHub_Project_Management_Board.html)

📋 Click to expand plain-text ASCII Board for manual copy-pasting

+--------------------+--------------------+--------------------------+------------------------------+--------------------+
|  PRODUCT BACKLOG   |  SPRINT 1 BACKLOG  |       IN PROGRESS        |         CODE REVIEW          |        DONE        |
+--------------------+--------------------+--------------------------+------------------------------+--------------------+
| [STORY-07]         | [STORY-01]         | [STORY-00]               |                              |                    |
| Snap-Grid Seat Map | Foundation, DB &   | Repo Foundation &        | (PR Review Gate)             | (Baseline State)   |
| Builder (Sprint 2) | RLS Policies       | Team Conventions         |                              |                    |
| Points: 10         | Est: 3d | Pts: 8   | Est: 3d | Pts: 5         | No pending PRs               | 0 stories complete |
|                    | Assignee: Adrian   | Assignee: Adrian         | Adrian squash-merges         | Pending merges     |
| [STORY-08]         |                    | WIP limit: 4             |                              |                    |
| Live Geo-Discovery | [STORY-02]         | Issue #49 - 2 of 7 tasks |                              |                    |
| & Map (Sprint 2)   | Design System &    |                          |                              |                    |
| Points: 8          | Public Shell       |                          |                              |                    |
|                    | Est: 2d | Pts: 5   |                          |                              |                    |
| [STORY-09]         | Assignee: Maria    |                          |                              |                    |
| Exact-Seat Holds & |                    |                          |                              |                    |
| Payments (Sprint 3)| [STORY-03]         |                          |                              |                    |
| Points: 10         | Multi-Role Auth &  |                          |                              |                    |
|                    | RBAC Middleware    |                          |                              |                    |
| [STORY-10]         | Est: 3d | Pts: 8   |                          |                              |                    |
| QR Check-in &      | Assignee: Luke     |                          |                              |                    |
| Moderation (S3)    |                    |                          |                              |                    |
| Points: 8          | [STORY-04]         |                          |                              |                    |
|                    | Seeker Dashboard & |                          |                              |                    |
|                    | Profile CRUD       |                          |                              |                    |
|                    | Est: 2d | Pts: 5   |                          |                              |                    |
|                    | Assignee: James    |                          |                              |                    |
|                    |                    |                          |                              |                    |
|                    | [STORY-05]         |                          |                              |                    |
|                    | Host Space Listing |                          |                              |                    |
|                    | CRUD               |                          |                              |                    |
|                    | Est: 3d | Pts: 8   |                          |                              |                    |
|                    | Assignee: Adrian   |                          |                              |                    |
|                    |                    |                          |                              |                    |
|                    | [STORY-06]         |                          |                              |                    |
|                    | Vitest Unit Tests  |                          |                              |                    |
|                    | Est: 2d | Pts: 5   |                          |                              |                    |
|                    | Assignee: Luke     |                          |                              |                    |
+--------------------+--------------------+--------------------------+------------------------------+--------------------+

### Story Card Summary Table for Board Import

| Card ID | Card Title & Description | Column | Assignee | Story Points | Time Est. | MoSCoW | Git Branch |
| --- | --- | --- | --- | --- | --- | --- | --- |
| STORY-00 | Repository Foundation & Team Conventions | In Progress | Adrian Seth Tabotabo | 5 / 10 | 3 Days | Must Have | feature/STORY-00-short-desc |
| STORY-01 | Foundation, Database Schemas & RLS Policies | Sprint 1 Backlog | Adrian Seth Tabotabo | 8 / 10 | 3 Days | Must Have | feature/STORY-01-database-rls |
| STORY-02 | Accessible Design System & Public Shell | Sprint 1 Backlog | Maria Faith Antigua | 5 / 10 | 2 Days | Should Have | feature/STORY-02-design-system |
| STORY-03 | Multi-Role Authentication & RBAC Guard | Sprint 1 Backlog | Luke Miguel Dongque | 8 / 10 | 3 Days | Must Have | feature/STORY-03-auth-rbac |
| STORY-04 | Seeker Portal & User Profile CRUD | Sprint 1 Backlog | James Niño Mandawe | 5 / 10 | 2 Days | Must Have | feature/STORY-04-seeker-profile-crud |
| STORY-05 | Host Portal & Space Listing CRUD | Sprint 1 Backlog | Adrian Seth Tabotabo | 8 / 10 | 3 Days | Must Have | feature/STORY-05-host-space-crud |
| STORY-06 | Automated Testing Suite & QA Validation | Sprint 1 Backlog | Luke Miguel Dongque | 5 / 10 | 2 Days | Should Have | feature/STORY-06-testing-qa |
| STORY-07 | Interactive Snap-Grid Seat Map Builder | Product Backlog | Team | 10 / 10 | 5 Days | Won’t Have (S1) | Defer to Sprint 2 |
| STORY-08 | Live Geo-Discovery & Map Tag Filters | Product Backlog | Team | 8 / 10 | 4 Days | Won’t Have (S1) | Defer to Sprint 2 |
| STORY-09 | Reserve-Now Seat Holds & Sandbox Payments | Product Backlog | Team | 10 / 10 | 5 Days | Won’t Have (S1) | Defer to Sprint 3 |
| STORY-10 | QR Check-in & Review Moderation | Product Backlog | Team | 8 / 10 | 4 Days | Won’t Have (S1) | Defer to Sprint 3 |

Issue mapping. STORY-00 #49 · STORY-01 #50 · STORY-02 #51 · STORY-03 #52 · STORY-04 #53 · STORY-05 #54 · STORY-06 #55 · STORY-07 #56 · STORY-08 #57 · STORY-09 #58 · STORY-10 #59. The STORY-00 tasks are TSK-00.1 #61 · TSK-00.2 #62 · TSK-00.3 #63 (merged, PR #68) · TSK-00.4 #64 (merged, PR #69) · TSK-00.5 #65 · TSK-00.6 #66 · TSK-00.7 #67.

## 6. Definition of Done (DoD) Checklist

A user story or sprint deliverable is formally marked as DONE only when satisfying all criteria below:

- Code Authorship & Branching: Implemented on its designated feature/STORY-xx-short-desc branch and squash-merged to main by Adrian, so the PR title and body become the commit.

- Design Gate: The design doc for the story (docs/design/STORY-xx-*.md) was merged before its code started, and this pull request links it.

- Local Checks: npm run check passes (typecheck, lint, format check, Vitest), and npm run db:test passes when SQL changed.

- CI: checks, pr-title, and db (once migrations exist) are green.

- Database Integrity & Security: All table mutations protected by verified Row-Level Security policies, with negative tests; no secret key exposed to the client.

- Accessibility & Responsiveness: WCAG 2.1 AA compliant color contrast (≥4.5:1), touch targets ≥48px×48px, keyboard focus rings, and no horizontal scrolling at 360, 768, and 1024px.

- Verified Criteria: Every acceptance criterion is ticked by the named person who verified it, and the pull request says how.

- Peer Code Review: The pull request has been reviewed and all review threads are resolved. The required approval count is 1; Adrian approves teammates’ PRs, and a teammate approves Adrian’s (D-014).

- Docs: Any document this change makes stale is updated in the same pull request.

- Tracking: The issue is closed and its card is in Done.