# StudyHub — Sprint 3 Plan (DRAFT): Reviews, Administration & Hardening

Course: CPEPE361 (Software Development 1)
Phase: Final Phase — Sprint 3
Sprint Duration: 2 Weeks (Weeks 10–11)
Development Lifecycle: Sprint 3 of 3

- Sprint 1 (Midterm): Foundation, Identity & Primary CRUD (Walking Skeleton)

- Sprint 2 (Prefinal): The Booking Journey — Discovery, Seat Map, Holds, Sandbox Payments & Check-in

- Sprint 3 (Final): Reviews, Administration & Hardening

## 0. Status: this is a draft

Status: DRAFT — not baselined. Nothing here is committed work.

Sprint 2 was baselined with every Must Have in the SRS, the whole booking journey from search to check-in (D-036). Holds, sandbox payments and check-in (STORY-09, STORY-10) moved there from this draft, and so did the Space verification queue, as STORY-15 (D-037). What is left for Sprint 3 is the Should Haves, whatever Sprint 2 carries over, and the hardening before the Final.

The same rules as for any draft apply:

- No card moves, no issue is created or re-scoped, and no code starts because of this document. The plan gate (D-016) still applies to every story here.

- Every estimate here is a guess. Sprint 2’s actual velocity, and what it carries over, will change it.

What makes it real. This becomes the Sprint 3 plan when, at the Sprint 2 review:

- Every Sprint 2 story is Done, or explicitly carried over into Sprint 3 with its points re-estimated. Sprint 2 has no cut line (D-036), so this review is where that is decided.

- The entry conditions in §2 hold.

- The open questions in §8 are settled.

- Adrian merges a pull request applying §10.

## 1. Sprint Goal

Make the booking journey trustworthy and finish the SRS’s functional scope: Seekers who actually visited can review a Space, and Administrators can moderate those reviews and oversee sandbox payments.

Concretely:

- Reviews after a completed check-in, with aggregates on the Space profile (FR-4.1, FR-4.2, D-009).

- Administration: review moderation, and sandbox payment oversight with refunds (FR-5.2, FR-5.3), on the /admin portal that STORY-15 creates in Sprint 2.

- Whatever Sprint 2 carries over, finished first.

- Getting ready for Week 12: the concurrency test in CI and the full journeys for every role (§9).

This sprint completes the SRS v2.0 functional scope. Nothing is left for a Sprint 4; Week 12 is hardening, not features (§9).

## 2. Entry Conditions — what Sprint 2 must have delivered

| Needed from Sprint 2 | Needed by |
| --- | --- |
| Completed check-ins on reservations (STORY-10) | STORY-13 |
| The Space profile, where reviews and aggregates appear (STORY-11) | STORY-13 |
| payments with paid, forfeited and refunded statuses (STORY-09, STORY-10) | STORY-14 |
| The /admin portal shell and its role guard (STORY-15) | STORY-14 |

## 3. Team Workload & Domain Distribution

| Developer | Role & Primary Domain | Draft responsibility |
| --- | --- | --- |
| Adrian Seth Tabotabo | Backend Lead & Database Architect | Sprint 2 carry-over; the reviews schema and policies with Maria; the production project |
| Luke Miguel Dongque | Auth & Security Specialist | Sprint 2 carry-over; the FR-2.5 concurrency test in CI; the security pass for Week 12 |
| Maria Faith Antigua | Frontend Design System Lead | STORY-13: review form gated on check-in, aggregate ratings, reporting a review |
| James Niño Mandawe | Portal Shells & QA Engineer | STORY-14: moderation and payment oversight, plus the final DoD verification |

Note on story numbering. STORY-13 (#78) and STORY-14 (#79) exist as issues. STORY-14 lost the verification queue to STORY-15 (#166) in Sprint 2, so it is re-estimated at Sprint 3 planning.

## 4. Sprint 3 Backlog with MoSCoW Prioritization

| Priority | Feature / User Need | Requirement | Description |
| --- | --- | --- | --- |
| Must Have (M) | Anything Sprint 2 carries over | — | Finished before any new story starts. |
| Should Have (S) | Reviews restricted to checked-in visitors | FR-4.1, D-009 | One review per completed visit. |
| Should Have (S) | Aggregate ratings and review reporting | FR-4.2 | Aggregates on the profile; reported reviews go to moderation. |
| Should Have (S) | Review moderation | FR-5.2 | A removed review leaves the profile and the aggregates. |
| Should Have (S) | Sandbox payment oversight and refunds | FR-5.3 | An Administrator reads payment records and issues a sandbox refund. |
| Could Have (C) | Rejection reasons and re-verifying edited Spaces | FR-5.1, D-027 | What STORY-15 left out. |
| Could Have (C) | Seeker reservation history | — | Past holds on the Seeker dashboard. |
| Could Have (C) | Email notification on hold confirmation | — | Only if Supabase’s free tier allows it without new cost. |
| Won’t Have (W) | Real-money settlement | Future release | SRS §1.2 and D-005: sandbox only, all semester. |
| Won’t Have (W) | Advance or scheduled bookings | Out of scope | D-001: current-state only. |
| Won’t Have (W) | Occupancy sensors | Out of scope | D-002: availability stays host-maintained. |

## 5. Draft Stories & Task Decomposition

### [STORY-13] Community Reviews & Ratings — issue #78

- Story: As a Seeker who actually visited, I want to review the amenities, so that other Seekers can trust what a space claims.

- Story Points: 8 / 10

- Time Estimate: 4 Days

- Assignee: Maria Faith Antigua

- Git Branch: feature/STORY-13-reviews

- MoSCoW: Should Have

- Requirements: FR-4.1, FR-4.2 · Decisions: D-009

#### Draft tasks

- Migration: reviews (Space FK, reservation FK, author FK, per-amenity ratings for noise, Wi-Fi reliability, cleanliness and comfort, body text, status).

- RLS enforcing D-009 in the database, not in the UI: an insert requires a reservation by this author at this Space with a completed check-in, and at most one review per reservation.

- pgTAP negatives: a user with no completed check-in cannot insert a review; a second review on the same reservation is rejected; another user gets 0 rows when editing someone else’s review.

- Review form on the Space profile, shown only when the Seeker is eligible.

- Aggregate ratings on the profile and in search results, excluding removed reviews.

- “Report this review”, flagging it for moderation (feeds STORY-14).

- Escape and sanitize all review text (SRS §3.5.2).

#### Draft acceptance criteria

- ☐ A user without a completed check-in cannot post a review for that Space.

- ☐ Each completed visit allows at most one review.

- ☐ Aggregate ratings on the profile match the visible, non-removed reviews.

- ☐ A reported review is flagged for Administrator moderation.

### [STORY-14] Administration Console — issue #79 (re-scoped)

- Story: As an Administrator, I want to moderate reported reviews and oversee sandbox payments, so that the platform stays trustworthy.

- Story Points: 8 / 10 (re-estimated at Sprint 3 planning)

- Time Estimate: 4 Days

- Assignee: James Niño Mandawe

- Git Branch: feature/STORY-14-admin-console

- MoSCoW: Should Have

- Requirements: FR-5.2, FR-5.3 · Decisions: D-005, D-013

Space verification (FR-5.1) moved to STORY-15 in Sprint 2. This story adds its queues to the /admin portal STORY-15 creates.

#### Draft tasks

- Moderation queue for reported reviews, with hide and remove, and removal excluded from aggregates (FR-5.2).

- Sandbox payment oversight: read fees paid, forfeited and refunded (FR-5.3).

- Sandbox refund action for when a Host cannot honour a paid hold, with the new status visible to the Seeker.

- pgTAP negatives: a Seeker or Host gets 0 rows from the admin queues and cannot remove a review or issue a refund.

- Final QA: Playwright journeys end to end (search → hold → pay → check in → review), and the DoD verification for the Final phase.

#### Draft acceptance criteria

- ☐ A removed review no longer appears on the profile or in the aggregates.

- ☐ A sandbox refund updates the payment status and is visible to the Seeker.

- ☐ A Seeker or Host attempting any admin action gets 0 rows and a rejected write.

## 6. Sequencing & Cross-Story Dependencies

| This story | Waits for | Because |
| --- | --- | --- |
| STORY-13 | Sprint 2’s STORY-10 (completed check-ins) | A review needs a completed check-in (D-009) |
| STORY-14 | STORY-13 task 1, and Sprint 2’s payments | Moderation and refunds need reviews and payments |

Anything Sprint 2 carries over goes first, because both stories build on it.

## 7. Project Management Board Mapping

The second column is renamed Sprint 3 Backlog when Sprint 3 starts (D-038). While this plan is a draft, both stories stay in Product Backlog.

| Card ID | Card Title | Column (today) | Assignee | Points | Time Est. | MoSCoW |
| --- | --- | --- | --- | --- | --- | --- |
| STORY-13 | Community Reviews & Ratings | Product Backlog | Maria Faith Antigua | 8 / 10 | 4 Days | Should Have |
| STORY-14 | Administration Console | Product Backlog | James Niño Mandawe | 8 / 10 | 4 Days | Should Have |

Draft sprint total: 16 points across 2 stories, plus Sprint 2’s carry-over.

## 8. Open Questions — settle these before baselining

- What does Sprint 2 carry over? Sprint 2 holds 55 points with no cut line (D-036), so its review decides what moves here, and who finishes it.

- Rejection reasons and re-verifying an edited Space. STORY-15 approves or rejects with no reason, and D-027 still lets a Host edit a Verified Space without sending it back to Pending. Does STORY-14 add both, or do they wait?

- Does Week 12 hardening get a card? If it does, it becomes a new story rather than being folded into STORY-14 (§9).

STORY-09’s own questions (the gateway, the two timers, the fee, lazy expiry, and whether a whole room takes one hold) moved to its design doc in Sprint 2.

## 9. After Sprint 3 — Week 12 hardening

The worksheet reserves Week 12 for QA and integration testing, and Weeks 13–14 for final evaluation and deployment. That is not a sprint and gets no story cards, but the Final phase depends on it:

- Full Playwright journeys for all three roles.

- The FR-2.5 concurrency test running in CI, not only locally.

- Performance against SRS §3.4: search under about 1 s, FCP under about 2 s, LCP under about 3 s, allowing for serverless cold starts.

- Classroom-scale concurrency, 30–50 simultaneous users, with no double-booking.

- Accessibility sweep against WCAG 2.1 AA across every route (SRS §3.2.2).

- A production Supabase project, created before the Final phase (D-017).

- Code authorship verification, and AI disclosure checked against D-020.

## 10. On Adoption — what the baselining pull request does

- Renames this file to StudyHub_Sprint_3_Plan.md, and deletes §0 and this section.

- Re-estimates against Sprint 2’s actual velocity, and folds in every carried-over story.

- Records §8’s answers in docs/DECISIONS.md, wherever they had real alternatives.

- Updates docs/course/README.md, and runs npm run docs:docx.

End of Sprint 3 Plan (DRAFT).